## Sheet1
iSearch Kelowna Group 2 Project Cost Estimate
Prepared by: Mohammed Alotaibi, Gurpyar Singh | Date: | Feb 23rd, 2018
Note: Change the WBS items and other entries to meet your project needs. This data is from Figure 7-1 of Schwalbe's text
Information Technology Project Management, Fourth Edition. Also make sure the formulas work properly based on the data you enter.
| # Units/Hrs. | Cost/Unit/Hr. | Subtotals | WBS Level 1 Totals | % of Total
WBS Items
1. Project Management |  |  |  | 8100 | 14.27%
1.1 Project manager | 81 | 20 | 1620
1.2 Project team members | 324 | 20 | 6480
Contractors (10% of software development and testing) |  |  | 0
2. Hardware |  |  |  | 22410 | 39.49%
2.1 Handheld devices | 4 | 5600 | 22400
2.2 Servers | 5 | 10 | 10
3. Software |  |  |  | 40 | 0.07049%
3.1 Licensed software | 1 | 40 | 40
3.2 Software development* |  |  | 0
4. Testing (10% of total hardware and software costs) |  |  |  | 0 | 0%
5. Training and Support |  |  |  | 16740 | 29.5%
5.1 Trainee cost | 27 | 20 | 540
5.2 Travel cost | 45 | 360 | 16200
5.3 Project team members | 0 | 0 | 0
6. Reserves (20% of total estimate) |  |  | 9458 | 9458 | 16.67%
Total project cost estimate |  |  |  | 56748
* See software development estimate

## Sheet2
* Software development
Contractor labor estimate | 3000 | 150 | 450000
Project team member estimate | 1920 | 75 | 144000
Total labor estimate |  |  | 594000
Function point estimate | Quantity | Conversion Factor | Function Points
External inputs | 10 | 4 | 40
External interface files | 3 | 7 | 21
External outputs | 3 | 5 | 15
External queries | 3 | 4 | 12
Logical internal tables | 6 | 10 | 60
Total function points |  |  | 148
Java 2 languange equivalency value |  |  | 46
Source lines of code (SLOC) estimate |  |  | 6808
Productivity *KSLOC^Penalty (person months) | 30.2659
Total labor hours (160 hours/month) | 4842.5507
Cost/labor hour ($120/hour) | 120
Total software development estimate | 581106.0898